## Sheet1
No. | Activit | Location | Member | Date | Year | Duration(Hour) | Deadline(mid noon) | Slack | Critical path time spend
A1 | Plan to finsh proposal |  |  |  | 2022 |  |  | 0
A1.1 | Recruit team | Zoom | Linsong | 2022-08-24 | 2022 | 2 | 2022-08-24 | 0 | 2
A1.2 | Decide leader of project, build basic communication | SDSU Daktronics 128 | All team | 2022-08-25 | 2022 | 1 | 2022-08-25 | 0 | 3
A1.3 | Standard work report & Assgin | SDSU Daktronics 128 | All team | 2022-08-30 | 2022 | 1 | 2022-08-30 | 0 | 4
A1.3.1 | Creating google document | SDSU Daktronics 128 | Fatoumata | 2022-08-30 | 2022 | 1 | 2022-08-30 | 0 | 5
A1.3.2 | Build basic FWBS | TBA | Linsong | 2022-08-30 | 2022 | 5 | 2022-09-01 | 0 | 10
A1.3.3 | Build basic Cost chart | TBA | Habiba | 2022-08-30 | 2022 | 5 | 2022-09-06 | 0 | 10
A1.3.4 | Build Milestone | TBA | Fatoumata | 2022-08-30 | 2022 | 2 | 2022-09-06 | 2 | 10
A1.4 | Meeting with client about FWBS | SDSU Daktronics 127 | All team | 2022-09-01 | 2022 | 1 | 2022-09-01 | 0 | 11
A1.4.1 | Discuss about meeting with client | SDSU Daktronics 128 | All team | 2022-09-02 | 2022 | 1 | 2022-09-02 | 0 | 12
A1.4.1.1 | Do changes base on client's suggest | SDSU Daktronics 128 | All team | 2022-09-02 | 2022 | 4 | 2022-09-05 | 0 | 16
A1.5 | Standard work report & Assgin | SDSU Daktronics 128 | All team | 2022-09-05 | 2022 | 1 |  | 0 | 17
A1.5.1 | Complete FWBS | TBA | Linsong | 2022-09-05 | 2022 | 4 | 2022-09-08 | 0 | 21
A1.5.2 | Complete milestone | TBA | Fatoumata | 2022-09-05 | 2022 | 1 | 2022-09-05 | 3 | 21
A1.5.3 | Work on discussed changes on Cost chart | TBA | Habiba | 2022-09-05 | 2022 | 1 | 2022-09-05 | 3 | 21
A1.6 | Standard work report & Assgin new work | SDSU Daktronics 127 | All team | 2022-09-08 | 2022 | 1 | 2022-09-08 | 0 | 22
A1.6.1 | Build activities table | TBA | Linsong | 2022-09-08 | 2022 | 5 | 2022-09-14 | 0 | 27
A1.6.2 | Build Risk table and Risk management plan | TBA | Habiba | 2022-09-08 | 2022 | 5 | 2022-09-14 | 0 | 27
A1.6.3 | Build Data management plan and security plan | TBA | Fatoumata | 2022-09-08 | 2022 | 5 | 2022-09-14 | 0 | 27
A1.7 | Standard work report, meet client and discuss changes | SDSU Daktronics 127 | All team | 2022-09-14 | 2022 | 1 | 2022-09-14 | 0 | 28
A1.7.1 | Build Activit graph, calculate CPA | TBA | Linsong | 2022-09-14 | 2022 | 5 | 2022-09-16 | 0 | 33
A1.7.2 | Build gantt chart, write project team organization, exchange Data mangement to sever selection |  | Fatoumata | 2022-09-14 | 2022 | 5 | 2022-09-16 | 0 | 33
A1.7.3 | Finsh build final cost table, estimate model | TBA | Habiba | 2022-09-14 | 2022 | 5 | 2022-09-16 | 0 | 33
A1.8 | Standard work report & Assgin new work | SDSU Daktronics 127 | All team | 2022-09-16 | 2022 | 1 | 2022-09-16 | 0 | 34
A1.8.1 | Write Deliverables, maintenance plan, warranty and terminology | TBA | Linsong | 2022-09-16 | 2022 | 2 | 2022-09-17 | 0 | 36
A1.8.2 | Write Cover letter, title and intro | TBA | Fatoumata | 2022-09-16 | 2022 | 2 | 2022-09-17 | 0 | 36
A1.8.3 | Write Alternatives, Terms of Acceptance and Conditions | TBA | Habiba | 2022-09-16 | 2022 | 2 | 2022-09-17 | 0 | 36
A1.9 | Standard work report, meet client and discuss changes | TBA | All team | 2022-09-17 | 2022 | 5 | 2022-09-17 | 0 | 41
A1.10 | Sumbit the Proposal | TBA | All team | 2022-09-18 | 2022 | 5 | 2022-09-18 | 0 | 46
A2 | Plan to finsh RD |  |  |  | 2022 |  |  | 0 | 46
A2.1 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-09-20 | 2022 | 1 | 2022-09-20 | 0 | 47
A2.1.1 | Build basic Appendix | TBA | Linsong | 2022-09-20 | 2022 | 3 | 2022-09-22 | 0 | 50
A2.1.2 | Write basic Introduction and General Description | TBA | Fatoumata | 2022-09-20 | 2022 | 3 | 2022-09-22 | 0 | 50
A2.1.3 | Write Functional Requirements | TBA | Habiba | 2022-09-20 | 2022 | 3 | 2022-09-22 | 0 | 50
A2.2 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-09-22 | 2022 | 1 | 2022-09-22 | 0 | 51
A2.2.1 | Finsh build Appendix and start Log of meeting etc. | TBA | Linsong | 2022-09-22 | 2022 | 5 | 2022-09-27 | 0 | 56
A2.2.2 | Finsh Functional Requirements and start Non-Funcitonal Requirements |  | Habiba | 2022-09-22 | 2022 | 5 | 2022-09-27 | 0 | 56
A2.2.3 | Finsh writing intro, Description and Change Control | TBA | Fatoumata | 2022-09-22 | 2022 | 5 | 2022-09-27 | 0 | 56
A2.3 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-09-27 | 2022 | 1 | 2022-09-27 | 0 | 57
A2.3.1 | Do changes base on client's suggest | TBA | All team | 2022-09-27 | 2022 | 5 | 2022-09-29 | 0 | 62
A2.4 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-09-29 | 2022 | 1 | 2022-09-29 | 0 | 63
A2.4.1 | Write Terms and Conditions, Table of Contents and Finalize RD | TBA | All team | 2022-09-29 | 2022 | 2 | 2022-09-30 | 0 | 65
A2.5 | Standard work report, meet client and discuss changes | TBA | All team | 2022-09-30 | 2022 | 1 | 2022-09-30 | 0 | 66
A2.6 | Do Final changes base on client's suggestion and sumbit RD | TBA | All team | 2022-09-30 | 2022 | 5 | 2022-10-03 | 0 | 71
A2.7 | Presentation of project | TBA |  | TBA | 2022 | 1 | TBA
A3 | Plan to finsh DS |  |  |  | 2022 |  |  | 0
A3.1 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-10-04 | 2022 | 1 | 2022-10-04 | 0 | 72
A3.1.1 | Write basic design | TBA | Linsong | 2022-10-04 | 2022 | 5 | 2022-10-06 | 0 | 77
A3.1.2 | Write basic intro | TBA | Fatoumata | 2022-10-04 | 2022 | 5 | 2022-10-06 | 0 | 77
A3.1.3 | Help others | TBA | Habiba | 2022-10-04 | 2022 | 5 | 2022-10-06 | 0 | 77
A3.2 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-10-06 | 2022 | 1 | 2022-10-06 | 0 | 78
A3.2.1 | Finsh writing design | TBA | Linsong | 2022-10-06 | 2022 | 5 | 2022-10-11 | 0 | 83
A3.2.2 | Finsh writing intro | TBA | Fatoumata | 2022-10-06 | 2022 | 3 | 2022-10-11 | 2 | 83
A3.2.3 | TBA | TBA | Habiba | 2022-10-06 | 2022 | TBA | 2022-10-11 | TBA | 83
A6 | Plan to finsh Coding of basic B-bay system |  |  | 2022-10-11 | 2022
A6.1 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-10-11 | 2022 | 1 | 2022-10-11 | 0 | 84
A6.1.1 | Build the basic framework of website for B-bay | TBA | Linsong | 2022-10-11 | 2022 | 10 | 2022-10-13 | 0 | 94
A3.3 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-10-13 | 2022 | 1 | 2022-10-13 | 0 | 95
A3.3.1 | continue working on DS base of clients suggestion | TBA | All team | 2022-10-13 | 2022 | 5 | 2022-10-18 | 0 | 100
A4 | Plan to finsh ATP |  |  |  | 2022 |  |  | 0
A4.1 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-10-18 | 2022 | 1 | 2022-10-18 | 0 | 101
A4.1.1 | Build Proposed system overview | TBA | Linsong | 2022-10-18 | 2022 | 10 | 2022-10-20 | 0 | 111
A4.1.2 | Build Test schedule and test sets | TBA | Fatoumata | 2022-10-18 | 2022 | 10 | 2022-10-20 | 0 | 111
A4.1.3 | Write Hardware Requirements and Software Requirements | TBA | Habiba | 2022-10-18 | 2022 | 10 | 2022-10-20 | 0 | 111
A4.2 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-10-20 | 2022 | 1 | 2022-10-20 | 0 | 112
A4.2.1 | Wtrite log of meetings etc, and Acceptance | TBA | Linsong | 2022-10-20 | 2022 | 10 | 2022-10-21 | 0 | 122
A4.2.2 | Write Individual test cases | TBA | Fatoumata | 2022-10-20 | 2022 | 10 | 2022-10-21 | 0 | 122
A4.2.3 | Write Appendix, intro and rest of APT | TBA | Habiba | 2022-10-20 | 2022 | 10 | 2022-10-21 | 0 | 122
A3.5 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-10-21 | 2022 | 1 | 2022-10-21 | 0 | 123
A3.5.1 | Do Final changes base on client's suggestion and sumbit DS |  | All team | 2022-10-21 | 2022 | 5 | 2022-10-23 | 0 | 128
A4.3 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-10-25 | 2022 | 1 | 2022-10-25 | 0 | 129
A4.3.1 | Do Final changes base on client's suggestion and sumbit ATP |  | All team | 2022-10-25 | 2022 | 5 | 2022-10-26 | 0 | 134
A5 | Plan to finsh STP |  |  |  | 2022 |  |  | 0
A5.1 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-10-27 | 2022 | 1 | 2022-10-27 | 0 | 135
A5.1.1 | Build table of test data and expected output of FWBS4 | TBA | Linsong | 2022-10-27 | 2022 | 10 | 2022-11-01 | 0 | 145
A5.1.2 | Build table of test data and expected output of FWBS2 | TBA | Fatoumata | 2022-10-27 | 2022 | 10 | 2022-11-01 | 0 | 145
A5.1.3 | Build table of test data and expected output of FWBS1 | TBA | Habiba | 2022-10-27 | 2022 | 10 | 2022-11-01 | 0 | 145
A6.2 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-11-01 | 2022 | 1 | 2022-11-01 | 0 | 146
A6.2.1 | Code FWBS1.1 and all sub functions of those | TBA | Habiba | 2022-11-01 | 2022 | 10 | 2022-11-03 | 0 | 156
A6.2.2 | Code FWBS2. Add merchandise and sub funcions of FWBS2. | TBA | Fatoumata | 2022-11-01 | 2022 | 10 | 2022-11-03 | 0 | 156
A6.2.3 | Code half of FWBS4. ,FWBS 4.1 and sub funcions of FWBS4.1 | TBA | Linsong | 2022-11-01 | 2022 | 10 | 2022-11-03 | 0 | 156
A6.3 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-11-03 | 2022 | 1 | 2022-11-03 | 0 | 157
A6.3.1 | Code FWBS1.3 and all sub functions of those | TBA | Habiba | 2022-11-03 | 2022 | 10 | 2022-11-08 | 0 | 167
A6.3.2 | Code FWBS2. Add merchandise and sub funcions of FWBS2. | TBA | Fatoumata | 2022-11-03 | 2022 | 10 | 2022-11-08 | 0 | 167
A6.3.3 | Code FWBS4. ,FWBS 4.1 and sub funcions of FWBS4.1 | TBA | Linsong | 2022-11-03 | 2022 | 10 | 2022-11-08 | 0 | 167
A5.2 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-11-08 | 2022 | 1 | 2022-11-08 | 0 | 168
A5.2.1 | Debug and test FWBS 4.1 | TBA | Linsong | 2022-11-08 | 2022 | 10 | 2022-11-10 | 0 | 178
A5.2.2 | Debug and test FWBS2 | TBA | Fatoumata | 2022-11-08 | 2022 | 10 | 2022-11-10 | 0 | 178
A5.2.3 | Debug and test FWBS1.1 and FWBS 1.3 | TBA | Habiba | 2022-11-08 | 2022 | 10 | 2022-11-10 | 0 | 178
A6.4 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-11-10 | 2022 | 1 | 2022-11-10 | 0 | 179
A6.4.1 | Code half of FWBS 1, FWBS1.2 and all sub functions of it | TBA | Habiba | 2022-11-10 | 2022 | 10 | 2022-11-15 | 0 | 189
A6.4.2 | Code half of FWBS 3. and all subfunctions of it | TBA | Fatoumata | 2022-11-10 | 2022 | 10 | 2022-11-15 | 0 | 189
A6.4.3 | Code FWBS 5.1, 5.6 and sub functions of them | TBA | Linsong | 2022-11-10 | 2022 | 10 | 2022-11-15 | 0 | 189
A6.5 | Standard work report, meet client and discuss changes | SDSU Daktronics 128 | All team | 2022-11-15 | 2022 | 1 | 2022-11-15 | 0 | 190
A6.5.1 | Code FWBS 5.2 and sub functions of them | TBA | Linsong | 2022-11-15 | 2022 | 10 | 2022-11-17 | 0 | 200
A6.5.2 | Code FWBS 3. and all subfunctions of it | TBA | Fatoumata | 2022-11-15 | 2022 | 10 | 2022-11-17 | 0 | 200
A6.5.3 | Code FWBS 1, FWBS1.2 and all sub functions of it | TBA | Habiba | 2022-11-15 | 2022 | 10 | 2022-11-17 | 0 | 200
A5.3 | Standard work report & Assgin new work | SDSU Daktronics 128 | All team | 2022-11-17 | 2022 | 1 | 2022-11-17 | 0 | 201
A5.3.1 | Debug and test FWBS 5.2 | TBA | Linsong | 2022-11-17 | 2022 | 10 | 2022-11-18 | 0 | 211
A5.3.2 | Debug and test FWBS 3 | TBA | Fatoumata | 2022-11-17 | 2022 | 10 | 2022-11-18 | 0 | 211
A5.3.3 | Debug and test FWBS 1 and FWBS 1.2 | TBA | Habiba | 2022-11-17 | 2022 | 10 | 2022-11-18 | 0 | 211
A5.8 | Standard work report, meet client and discuss changes | TBA | All team | 2022-11-18 | 2022 | 1 | 2022-11-18 | 0 | 212
A5.8.1 | Write rest of SPT base on client's suggestion | TBA | All team | 2022-11-18 | 2022 | 5 | 2022-11-18 | 0 | 217
A5.9 | Do Final changes base on client's suggestion and sumbit STP | TBA | All team | 2022-11-18 | 2022 | 5 | 2022-11-21 | 0 | 222
A6.6 | Presentation of project's current process | TBA | All team | TBA | 2022 | 1
A7 | Plan to finsh Coding of the whole B-bay system | [6 empty] | 0
Formulas:
Deadline(mid noon) = 表2[[#This Row],[Date]]