## Sheet1
Milestone No. | Milestone Name | Responsibility | Date
M1 | Get request from client | Qnet&prof.Shin Company | 2022-08-22
M2 | Complete Proposal | Qnet | 2022-09-19
M3 | Document all requirements | Qnet | 2022-10-03
M4 | Project presentation 1 | Qnet | 10/TBA/2022
M5 | Complete desgin specification | Qnet | 2022-10-23
M6 | Complete acceptance test plan | Qnet | 2022-10-26
M7 | Complete system test plan | Qnet | 2022-11-01
M8 | Complete basic B-bay system | Qnet | 11/18/2022
M9 | Complete testing basic B-bay system | Qnet | 2022-11-21
M10 | Project presentation 2 | Qnet | 2022-12-08
M11 | Complete all proposaled B-bay system | Qnet | 2022-12-18
M12 | Complete testing B-bay system | Qnet | 2022-12-28
M13 | Project presentation 3 & offcial terms signing | Qnet&prof.Shin Company | 2022-12-30