## Sheet1
Test Input |  | Expected outcome | Actual outcome | P/F
Using ipad air 4
Using iphone xr
No. | FWBS No. | Test description | Executor | Date | P/F
ST1 | 1.1 | Create administrator account | Linsong | 2023-05-01
ST2 | 1.3 | Create Buyer/Seller account | Habiba | 2023-05-02
ST3 | 1.2 | Login with Buyer/seller account | Fatoumata | 2023-05-03
ST4 | 2 | Create a request of auction or consignment | Linsong | 2023-05-07
ST5 | 3 | Check the function of the 3 types of lists | Fatoumata | 2023-05-09
ST6 | 4.1 | Try search a item in Home page | Habiba | 2023-05-12
ST7 | 4.2 | Check if Notificaiton/FAQs/Policy is working | Fatoumata | 2023-05-13
ST8 | 5.4 | Check if wish list display correctly | Linsong | 2023-05-16
4.3
ST9 | 5.3 | Check if Cart list is working | Habiba | 2023-05-17
4.4
ST10 | 5.5 | Try if chat allow communication to right target | Habiba | 2023-05-20
4.7
ST11 | 4.8 | Check if history purchase display correctly | Fatoumata | 2023-05-21
ST12 | 5.1 5.3 5.4 5.6 | Check if merchandise info display correctly | Linsong | 2023-05-22
ST13 | 5.2 | Try to Buy a consignment/auction item | Habiba | 2023-05-23
ST14 | 5.5 | Check if chat with seller function works | Habiba | 2023-05-27